ZeroW

Smart Campus & Urban Waste Management Platform

Business Concept Document

Prepared for: National Case Study Competition — Theme: Social Entrepreneurship

| Team | Team Decode |
| --- | --- |
| Institution | Aligarh Muslim University (AMU) |
| Initial Markets | Aligarh & Delhi → Pan-India Expansion |
| Sector | WasteTech / GovTech / Circular Economy |
| Date | July 2026 |

This document consolidates the problem statement, market sizing, product, pricing, competitive, AI, revenue, financial, legal, and gap analysis for the ZeroW venture, intended to give complete concept clarity for pitch and evaluation purposes.

# Table of Contents

# 1. Executive Summary

India generates over 62 million tonnes of municipal solid waste annually, and large residential campuses and dense urban wards remain among the weakest links in that chain — waste is generated at high density but managed through fragmented, manual, and unaccountable systems. ZeroW is a student-founded, technology-enabled waste management venture that begins on the Aligarh Muslim University (AMU) campus and is designed from day one to scale into a municipal and institutional SaaS platform across Delhi and, eventually, pan-India.

The venture combines three elements that most incumbents offer only in part: (1) a low-cost, QR-based hardware layer for bin-level accountability, (2) a software layer that digitises attendance, ticketing, and reporting, and (3) an AI layer that verifies segregation quality and predicts waste generation rather than simply logging it after the fact. Revenue is designed as a hybrid of grant/CSR-funded capital expenditure and recurring SaaS, compliance, and marketplace commission revenue — avoiding the common social-enterprise trap of permanent dependence on donor funding.

- Problem: Segregation failure, overflowing bins, unmanaged food/garden/biomedical/e-waste, and no accountability framework linking students, sanitation staff, departments, and municipal bodies.

- Solution: ZeroW Student Committee (governance) + ZeroW Web/App (QR attendance, ticketing, dashboards, leaderboard) + AI-based segregation verification and forecasting.

- Initial market: AMU campus (~40,000 student population, ~15,000 resident students, ~7,300 staff, 117 departments, 1,269 hospital beds) generating an estimated 22 metric tonnes of waste per day.

- Expansion market: Delhi as a metro pilot, followed by a pan-India rollout to tier-1/tier-2 campuses, hospitals, and municipal wards.

- Revenue logic: Grants and CSR fund capital expenditure (bins, sensors, launch); recurring SaaS/compliance fees and marketplace commissions fund operations and generate margin.

- Ask: Seed funding / UGC Green Fund support for Phase 1 pilot, and institutional partnership with AMU administration and the Aligarh Municipal Corporation for Phase 2.

# 2. Problem Statement & Positioning

## 2.1 The Core Problem

Waste management on large residential campuses and in dense Indian urban wards fails not because bins are absent, but because there is no accountable, data-backed system connecting the people who generate waste, the staff who collect it, and the authorities who are responsible for its downstream processing. This creates a cycle where waste is generated faster than it is responsibly cleared, and every stakeholder can credibly say the failure lies with someone else.

2.1.1 Segregation Issues

Students and staff routinely dispose of food, plastic, paper, and hazardous waste in the same bin. This single failure point makes every downstream process — composting, recycling, safe biomedical disposal — structurally impossible, regardless of how much processing infrastructure exists.

2.1.2 Overflowing and Misplaced Bins

Bins in hostels, messes, and common areas overflow quickly because there is no real-time visibility into fill levels or cleaning schedules. Poor placement compounds the problem: when a bin is inconveniently located, people litter instead of walking to it, and there is currently no mechanism to flag or correct this.

2.1.3 Mess, Hostel, and Canteen Food Waste

Large volumes of organic waste from messes, hostels, and canteens go to landfill daily with no composting or reuse system in place, despite being highly compostable. This is also the segment with the fastest odour and hygiene deterioration if collection is delayed.

2.1.4 Hospital (Biomedical) Waste

With 1,269 hospital beds on campus (JNMCH), biomedical waste is a distinct and higher-risk category. Inadequate segregation and monitoring gaps mean infectious and non-infectious waste often get mixed, which is both a health risk and a regulatory compliance exposure under India's Biomedical Waste Management Rules.

2.1.5 E-Waste, Garden Waste, and Open Potholes

Electronic waste is discarded without formal recycling channels, causing long-term soil and water contamination risk. Garden waste from AMU's expansive lawns blocks drains and causes hygiene issues due to the absence of on-campus composting infrastructure. Open potholes, while not waste in the traditional sense, are flagged in this concept as a related civic-infrastructure failure that the same reporting and accountability layer can help surface to the relevant authority.

## 2.2 Root Causes (Key Challenges)

- No segregation habit at source — people mix waste types because there is no immediate consequence or convenient alternative.

- No incentive structure — there is no gamification, recognition, or accountability mechanism to reward correct disposal behaviour.

- Low awareness — campaigns, where they exist, are minimal and largely ineffective at changing daily habits.

- Poor bin availability and placement — inadequate infrastructure pushes people toward indiscriminate littering.

- No composting infrastructure — garden and food waste that could be processed on-site instead goes to landfill.

- Fragmented responsibility — departments, sanitation staff, garden staff, and municipal authorities operate independently with no shared framework, standardised reporting method, or real-time information sharing.

## 2.3 Positioning Statement

ZeroW is positioned as: “The accountability layer for Indian institutional and municipal waste management — a low-cost, QR-and-AI-based system that makes waste visible, measurable, and traceable, starting with campuses and scaling to cities.” This distinguishes ZeroW from (a) pure-play waste processors who handle waste but not accountability, and (b) generic civic-complaint apps who handle reporting but have no domain-specific waste workflow, segregation verification, or municipal compliance layer.

ZeroW is not positioned as a waste collection or disposal company — it does not own trucks, landfills, or processing plants. It is positioned as the software and governance layer that makes existing waste collection systems (whether run by a university, a municipal corporation, or a private contractor) accountable, measurable, and improvable. This is a deliberate, capital-light positioning choice: it lets ZeroW scale across institutions and cities without the capex burden that sinks most physical waste-processing ventures.

# 3. Global Market Analysis & Expansion Opportunities

## 3.1 Global Context

The global waste management market is valued at approximately USD 2.49 trillion in 2026 and is projected to reach roughly USD 3.68 trillion by 2033, growing at a CAGR of about 5.7%. Within this, the specific smart waste management segment — IoT-enabled bins, sensor-based monitoring, and AI-driven route and sorting optimisation — is far smaller but growing much faster: estimated at roughly USD 3.4 billion in 2026, projected to reach about USD 5.8 billion by 2030 at a CAGR near 14.4%. Asia-Pacific holds the largest regional share of the overall waste management market (around 58%) and is also the fastest-growing region for smart waste solutions, driven by urbanisation and government-led digitisation of civic services.

This gap — a multi-trillion-dollar core industry with a comparatively nascent, fast-growing “smart” layer — is exactly where ZeroW positions itself: not competing with the trillion-dollar physical collection/disposal industry, but building the thin, high-growth digital accountability layer on top of it.

## 3.2 India Market Context

India's waste management market is estimated at roughly USD 14.3 billion in 2026, expected to grow to around USD 18.9–19 billion by 2031–32 (estimates across research houses range from a CAGR of about 4.8% to 7.1% depending on scope and methodology). Municipal solid waste is the largest single category, accounting for roughly 57% of the market, and collection remains the largest service line by revenue share — confirming that the industry today is still built around physical hauling rather than data or accountability.

A significant regulatory tailwind exists: India's new Solid Waste Management Rules, effective April 2026, mandate four-stream segregation at source (wet, dry, sanitary, and special waste) and place stronger direct responsibility on urban local bodies for collection, transportation, and processing. This directly increases institutional and municipal willingness to pay for segregation-verification and compliance-reporting tools — the exact wedge ZeroW is built around.

## 3.3 Expansion Opportunity Map

| Phase | Geography | Rationale |
| --- | --- | --- |
| Phase 0 (Pilot) | AMU Campus, Aligarh | Controlled environment, existing fieldwork and asset data, founder access to administration |
| Phase 1 | Aligarh city (municipal wards) | Adjacent geography, existing local relationships, Aligarh Municipal Corporation as pilot partner |
| Phase 2 | Delhi (select wards / institutions) | High waste-generation density, strong CSR/UGC funding access, high media and investor visibility |
| Phase 3 | Tier-1 university campuses pan-India | Repeatable model — similar asset structure (departments, hostels, hospitals) across large residential universities |
| Phase 4 | Tier-2 municipal corporations | SWM Rules 2026 compliance pressure creates a national buyer base for reporting/compliance SaaS |

## 3.4 Why Expansion Beyond Aligarh Is Credible, Not Just Assumed

The transferability of the model rests on three structural similarities that hold across Indian institutions and municipalities: (a) waste is generated by a similar mix of hostels/residences, departments/offices, canteens, and a hospital or clinic, so the same asset-register logic applies; (b) sanitation staffing is typically informal or semi-formal in all these settings, so QR-based attendance verification solves the same problem everywhere; and (c) the new national SWM Rules (2026) create a uniform compliance requirement across states, rather than a patchwork of local rules that would force a different product for every city. The genuine variable across geographies is municipal governance capacity and procurement cycles — which affects sales cycle length, not product-market fit.

# 4. Market Estimation (TAM / SAM / SOM)

Market estimation is built bottom-up from AMU's own asset register and top-down from India's institutional and municipal waste-tech spend, triangulated against the smart waste management market data above.

## 4.1 Total Addressable Market (TAM)

TAM is defined as the total spend potential across India's residential university campuses, large hospitals, and municipal corporations that would need a waste accountability/compliance layer under the SWM Rules, 2026. India has roughly 1,100+ universities and thousands of degree colleges with residential components, ~700 municipal corporations/councils, and tens of thousands of hospitals with biomedical waste obligations. Even a conservative estimate of addressable institutional + municipal software/service spend in this category places TAM in the range of USD 400–600 million annually within India alone, growing in line with the ~14% CAGR of the smart waste management segment.

## 4.2 Serviceable Addressable Market (SAM)

SAM narrows this to institutions and municipal wards realistically reachable through ZeroW's go-to-market motion (direct university partnerships, municipal corporation pilots, NGO tie-ups) over a 5-year horizon: large residential universities (approx. 250–300 nationally), major hospitals attached to them, and municipal wards in 2–3 target states (Uttar Pradesh, Delhi NCR, and one additional state post Series-A). This is estimated at roughly USD 40–60 million annually.

## 4.3 Serviceable Obtainable Market (SOM) — 5-Year Target

SOM is the realistic capture target given ZeroW's current stage, team size, and funding: AMU + 4–6 additional university campuses + 1–2 municipal ward pilots in Delhi/Aligarh by Year 3, expanding to 15–20 institutions and 3–5 municipal partnerships by Year 5.

| Metric | AMU Campus (Base) | Year 3 Target | Year 5 Target |
| --- | --- | --- | --- |
| Institutions/wards covered | 1 | 6–8 | 18–22 |
| Population covered (approx.) | ~55,000 | ~350,000 | ~1.1 million |
| Daily waste under system (MT) | ~22 | ~140 | ~450 |
| Estimated annual recurring revenue | — (pilot) | ₹0.6–0.9 Cr | ₹3–4.5 Cr |

These figures are directional planning estimates, not audited projections, and should be revisited once Phase 1 pilot data (actual conversion cost, actual willingness-to-pay per institution) is available.

## 4.4 AMU Campus — Base Waste Data

| Asset Type | Count / Estimate | Waste Relevance |
| --- | --- | --- |
| Total waste generated per day | ~22 metric tonnes | Baseline for pilot sizing |
| Waste from resident students | ~8.25 metric tonnes/day | ~15,000 residing students |
| Waste from staff | ~4.01 metric tonnes/day | ~7,300 teaching & non-teaching staff |
| Departments | 117 | Academic and office waste |
| Faculties | 13 | Coordination and policy units |
| Halls of Residence | 20 | Highest daily waste generators |
| JNMCH Hospital beds | 1,269 | Biomedical and general waste |

# 5. Proposed Solution

## 5.1 ZeroW Student Committee — Governance Layer

A student-led ZeroW Committee is formed starting with the Department of Business Administration, with gradual expansion across all 117 AMU departments. Each department eventually has its own ZeroW Committee unit, and the overall committee acts as the bridge between students, cleaning staff, administration, and municipal bodies — directly addressing the fragmented-responsibility root cause identified in Section 2.

- Key responsibility 1: Drive awareness and behaviour change through campus campaigns and events.

- Key responsibility 2: Monitor cleanliness and waste segregation compliance.

- Key responsibility 3: Manage cleaning staff coordination and scheduling.

- Key responsibility 4: Oversee installation and maintenance of segregated bins.

- Key responsibility 5: Manage green funds and committee resources.

## 5.2 ZeroW Web/App — Technology Layer

The ZeroW platform is a student-driven digital system designed to turn campus (and eventually municipal) waste management into a transparent, accountable, and participative process.

| Feature | What it does | Problem it solves |
| --- | --- | --- |
| Role-based login | Separate interfaces for students, cleaners, and administrators | Responsibility, traceability, and clean data |
| Smart dashboard | Real-time snapshot of total waste generated, points earned, and overall cleanliness performance | Makes waste “measurable” instead of invisible |
| High waste zone identification | Flags canteens, hostels, walkways, and event zones that consistently generate more waste | Focuses action on real hotspots instead of assumptions |
| Scan & report (QR attendance) | Cleaners scan a QR code on each bin after cleaning; time and location auto-logged | Removes manual registers and supervision pressure |
| Ticket raising | Students report overflow/issues in one tap; ticket auto-routes to committee and cleaners | Closes the loop between complaint and resolution |
| Map view & leaderboard | Visualises waste intensity across zones; ranks departments, students, and clean zones | Creates a shared, gamified cleanliness goal |

## 5.3 Before vs. After ZeroW

| Dimension | Before ZeroW | After ZeroW |
| --- | --- | --- |
| Student role | Spectators | Decision-makers and reporters |
| Cleaning verification | Manual, unsupervised | QR-verified, time-stamped |
| Data availability | None | Live dashboards |
| Accountability | None | Campus-wide, tracked by role |

# 6. Product Development

## 6.1 Development Roadmap

| Phase | Milestone | Demonstrated Impact |
| --- | --- | --- |
| Phase 1 | Formation of ZeroW Committee | Student-led governance body with clear ownership and accountability |
| Phase 1 | Launch of awareness initiatives | Shifts mindset from waste disposal to waste responsibility |
| Phase 1 | Development of the ZeroW App | Digitises waste reporting and monitoring, eliminating manual registers |
| Phase 2 | Installation of QR-coded segregation bins | Enables measurable separation of organic and non-biodegradable waste |
| Phase 2 | Appointment of paid, dignified workers | Formalises labour instead of relying on informal/unpaid effort |
| Phase 2 | QR-based attendance tracking | Replaces physical supervision with real-time, tamper-resistant verification |
| Phase 2 | Closed-loop waste processing | Organic waste converted to manure; non-biodegradable waste enters recycling streams |

## 6.2 Minimum Viable Product (MVP) Scope

The MVP for the AMU pilot should be intentionally narrow: QR-tagged bins in 2–3 high-waste zones (a hostel mess, a canteen, and one academic block), a basic role-based web app covering login, scan-and-report, and ticket raising, and a manually-compiled weekly dashboard rather than a fully automated one. This keeps Phase 1 capital expenditure inside the already-budgeted ₹1.2 lakh fixed cost while proving the core loop: segregation → QR verification → ticket resolution → dashboard visibility.

## 6.3 Technical Architecture (High Level)

- Frontend: mobile-responsive web app (role-based views for student / cleaner / admin).

- Backend: cloud-hosted database logging scans, tickets, and attendance events with timestamp and geo-tag.

- Hardware: static QR codes on bins in Phase 1 (near-zero marginal cost); optional low-cost fill-level sensors in Phase 2 for high-traffic zones only, to control capex.

- AI layer (see Section 10): image-based segregation classifier, ticket-triage NLP, and waste-forecasting model, added once sufficient usage data exists (approx. Month 4–6 of Phase 1).

## 6.4 What Is Currently Missing From the Product Plan

The existing concept does not yet specify: (a) an offline/low-connectivity fallback for cleaning staff who may not have reliable smartphone data access, (b) a data-privacy and retention policy for attendance and location logs of workers, and (c) a defined process for what happens when a ticket goes unresolved beyond a set SLA. These should be addressed before pilot rollout, and are elaborated in Section 12 (Gap Analysis).

# 7. Price and Place

## 7.1 Pricing Strategy

ZeroW uses tiered, buyer-differentiated pricing rather than a single price point, because the willingness-to-pay and budget cycle differ sharply between a university department, a hospital, and a municipal corporation.

| Buyer segment | Pricing model | Indicative price point |
| --- | --- | --- |
| University department/institution | Flat annual SaaS licence per campus | ₹1.5–2.5 lakh/year per mid-size campus |
| Hospital / biomedical unit | Compliance-reporting SaaS + per-bed fee | ₹20–40/bed/month |
| Municipal corporation | Per-ward monthly licence, tiered by ward population | ₹15,000–40,000/ward/month |
| Recyclers / compost buyers | Commission on transaction value via marketplace | 5–10% of transaction value |
| CSR/Grant funders | One-time capex sponsorship, not recurring | Project-based (₹1–10 lakh per site) |

This tiering intentionally keeps the AMU pilot near-free or grant-funded (to prove the model without a sales cycle) while establishing the actual paid pricing tiers that will apply once ZeroW pitches to a second university, a hospital, or a municipal corporation directly.

## 7.2 Place / Go-to-Market Channels

- Direct institutional partnerships: starting with AMU administration, then approaching similarly structured residential universities (a repeatable sales motion given similar asset registers).

- Municipal corporation pilots: beginning with Aligarh Municipal Corporation (existing local relationships) before approaching Delhi wards, using the SWM Rules 2026 compliance mandate as the entry point.

- NGO and CSR partnerships: for both funding (capex) and on-ground implementation support in new geographies.

- UGC Green Fund and government sustainability schemes: as a funding and legitimacy channel, particularly for university expansion.

- Word-of-mouth / inter-university networks: student committees and placement/administrative networks (a channel the founding team already has direct access to) as a low-cost expansion mechanism.

# 8. Competitive Landscape

India's organised waste management sector already has several established players, but each occupies a different position in the value chain than ZeroW. Understanding this precisely is important because judges and investors will specifically ask how ZeroW differs from existing solutions.

| Player | Core model | How ZeroW differs |
| --- | --- | --- |
| Saahas Zero Waste (Bengaluru, est. 2013) | End-to-end physical waste management for bulk generators (corporates, apartments, institutions); EPR compliance; owns processing/MRF facilities | ZeroW is asset-light software/governance layer, not a waste processor; targets campuses/municipalities first, not corporate bulk generators |
| Recykal (Hyderabad, est. 2017) | B2B digital marketplace connecting waste generators, aggregators, and recyclers; EPR credit trading | Recykal digitises the trade of waste; ZeroW digitises the accountability and verification of collection and segregation at the point of generation |
| Nepra Resource Management | Integrated industrial/hazardous waste management services | Nepra is service-delivery focused; ZeroW is a technology layer that can sit on top of any service provider, including Nepra-type operators |
| Generic municipal civic-complaint apps (e.g. Swachhata-App style tools) | General civic issue reporting to municipal bodies | ZeroW has a waste-specific workflow: QR-linked bin identity, cleaner attendance verification, and segregation-quality checks — not just a complaint inbox |
| Informal waste-picker networks | Manual, unorganised collection and sorting | ZeroW aims to formalise and dignify this workforce through paid roles and verified attendance rather than compete with or displace it |

## 8.1 Competitive Positioning Summary

Most incumbents are strong on either physical processing (Saahas, Nepra) or waste trading (Recykal), but none combine QR-based worker accountability, student/citizen-facing gamified reporting, and AI-based segregation verification into a single low-capex platform aimed first at institutions and then municipalities. ZeroW's realistic competitive moat is not the QR/ticketing layer alone (which is replicable) but the combination of (a) an embedded student/citizen governance community that most vendors do not have, and (b) the AI segregation-verification layer described in Section 10, once built and validated with real accuracy data.

## 8.2 Barriers to Entry and Risk of Replication

The technology layer (QR + dashboard) has a low barrier to entry and could be replicated by a competent developer team within months. ZeroW's more durable advantages are: an established institutional relationship (AMU administration access), a proprietary dataset of segregation and attendance behaviour once the pilot runs, and the student-committee governance model, which is harder to replicate quickly because it depends on organisational trust and campus relationships, not just code.

# 9. AI Integration and Growth Strategy

## 9.1 Where AI Adds Genuine Value (Not Just Branding)

The current QR-and-dashboard system logs activity but does not verify quality or predict demand. AI is introduced specifically to close that gap, in four prioritised applications:

- 1. Segregation verification (computer vision): When a cleaner scans a bin's QR code, they also capture a photo. A lightweight image classifier (wet/dry/biomedical/mixed) checks whether segregation actually happened, turning “verified cleaning” into “verified correct segregation” — this is the single highest-value AI feature because it is what compliance-focused institutional and municipal buyers will pay for.

- 2. Predictive overflow and route optimisation: Once a few weeks of fill-rate and ticket data exist, a time-series model predicts when specific bins will overflow, feeding a basic route-optimisation layer so collection staff move to where waste actually is, not a fixed round.

- 3. Ticket triage (NLP): Automatically classifies and prioritises student/citizen-raised tickets (overflow vs. hazard vs. general complaint) and routes them to the correct cleaning unit, reducing manual dispatch.

- 4. Anomaly detection on attendance: Flags implausible scan patterns (impossible time/location gaps, clustering) to substantiate the “tamper-resistant attendance” claim with an actual verification mechanism, rather than asserting it on the strength of the QR code alone.

- 5. Compost/recyclables demand forecasting: Forecasts organic waste volume to estimate compost output and match it to buyer demand (nurseries, farms, landscaping firms) — this directly connects the operational data to the revenue model in Section 10.

## 9.2 AI Rollout Sequencing

AI features should not be built before there is usage data to train or validate them. The recommended sequence is: Months 1–3 (manual/rule-based ticket routing and a simple dashboard, no AI); Months 4–6 (introduce the segregation-verification classifier once a few thousand bin-scan photos exist from Phase 1); Months 7–12 (introduce predictive overflow/route optimisation and anomaly detection once sufficient historical scan and ticket data has accumulated); Year 2 onward (compost/recyclables demand forecasting, once marketplace transactions exist to forecast against).

## 9.3 Growth Strategy

- Land-and-expand within institutions: start with one department/hostel, prove the loop, then expand to all 117 AMU departments before approaching a second university.

- Replicate the model across similarly structured universities: using AMU's own asset-register format (departments, halls of residence, hospital beds) as a repeatable diagnostic and sales tool for other residential universities.

- Enter municipal wards through the SWM Rules 2026 compliance requirement: position ZeroW as the fastest way for a municipal corporation to demonstrate compliance with the new four-stream segregation mandate.

- Build defensibility through data: the longer ZeroW operates in a location, the better its AI models perform on that location's specific waste patterns, creating a data moat against faster-moving but data-poor competitors.

# 10. Revenue Model

The current concept document lists costs but not revenue — relying only on a UGC Green Fund grant ask. For a social-entrepreneurship competition and for real sustainability, ZeroW needs a hybrid model where grants and CSR fund one-time capital expenditure, while recurring SaaS, compliance, and marketplace revenue fund operations and create a profit margin.

| Revenue stream | Who pays | Nature | Why it works |
| --- | --- | --- | --- |
| B2G SaaS licensing | Municipal corporations | Recurring (monthly/annual, per ward) | Cities need this for SWM Rules 2026 compliance and Swachh Survekshan rankings |
| B2B compliance SaaS | Hospitals, universities, corporate campuses | Recurring (per-bed / per-campus annual fee) | Biomedical/general waste audit trails are a regulatory requirement, giving high willingness-to-pay |
| Marketplace commission | Recyclers/kabadiwalas buying aggregated dry waste | Transaction-based (5–10% commission) | Platform aggregates supply and takes a cut, without owning recycling infrastructure |
| Compost sales | Farmers, nurseries, landscaping firms | Transaction-based | Monetises the organic-to-manure output already claimed as an impact metric |
| CSR funding | Corporates (Companies Act CSR mandate) | One-time / project-based (capex only) | Funds bin installation and labour setup without creating ongoing dependency |
| Certification-as-a-service | Institutions seeking “Green Campus” status | Annual fee | Ties into NAAC/Swachh Survekshan-linked institutional rankings that AMU already values |

One-line revenue logic: Grants and CSR fund the capex; SaaS and compliance fees fund the opex; marketplace commissions and compost sales create the profit margin. This is a genuine hybrid model, not a charity ask dressed as a business plan.

## 10.1 Illustrative Unit Economics (Per Institution, Post-Pilot)

| Item | Estimate |
| --- | --- |
| Annual SaaS licence (mid-size university) | ₹1.5–2.5 lakh |
| Estimated annual servicing cost (support, updates, minor hardware replacement) | ₹40,000–60,000 |
| Estimated gross margin per institution (Year 2+) | 60–70% |
| Payback period on institutional acquisition cost | 6–12 months, assuming a direct-sales, low-CAC model |

# 11. Financials

## 11.1 Phase 1 & Phase 2 Budget (AMU Pilot)

| Phase | Line item | Amount |
| --- | --- | --- |
| Phase 1 | Awareness & workshops (posters & banners, two events/month) | ₹8,000/month |
| Phase 2 | Dustbins for segregation | ₹1,20,000 (one-time) |
| Phase 2 | Labour (20 workers) | ₹8,000/month |
| Both | Miscellaneous | ₹30,000 |

| Cost category | Amount |
| --- | --- |
| Total fixed cost | ₹1,20,000 |
| Total variable cost | ₹46,000 |

## 11.2 Funding Sources for Phase 1

- UGC Green Fund (primary grant target for capex).

- Certificates and awards to be provided by the municipal corporation (non-cash institutional support).

- CSR co-funding (recommended addition — not yet in the original budget) to reduce single-source grant dependency.

## 11.3 What the Financials Currently Lack (and Should Be Added)

The original budget is a capex/opex cost sheet for a single pilot; it is not yet a financial model. To give real concept clarity and to be credible in front of judges or investors, the following should be added before the next pitch iteration:

- A revenue line: even directional SaaS/compliance/marketplace revenue estimates (see Section 10.1) so costs are matched against income, not shown in isolation.

- A break-even timeline: at what month/institution count does cumulative revenue cover cumulative cost.

- A 3–5 year projection: showing cost and revenue scaling as ZeroW expands from 1 campus to the Section 4 SOM targets.

- A cost-per-institution acquisition estimate: to justify the unit economics in Section 10.1 and support the payback-period claim.

- A sensitivity/downside case: e.g., what happens if the UGC grant is delayed or partially approved — shows funding-risk awareness.

# 12. Gap Analysis

This section consolidates the gaps identified across every section above, so the team has a single checklist before the next pitch or build iteration.

| Area | Current state | Gap | Recommended fix |
| --- | --- | --- | --- |
| Revenue model | Grant-only ask (UGC Green Fund) | No recurring/hybrid revenue model shown | Add the Section 10 hybrid SaaS + marketplace + CSR model |
| Financial model | Single-pilot cost sheet | No revenue, break-even, or multi-year projection | Build a 3–5 year model per Section 11.3 |
| Competitive landscape | Not addressed in original deck | No comparison to Saahas, Recykal, Nepra, or civic-complaint apps | Use Section 8 comparison table; be ready to answer “how are you different” |
| AI claims | “Smart” and “tamper-proof” asserted without mechanism | QR logging alone does not constitute AI or tamper-proofing | Add segregation-verification CV model and anomaly detection per Section 9 |
| Legal/regulatory framing | Not addressed | No mention of SWM Rules, Biomedical Waste Rules, or data protection | Add Section 13 compliance framing to the pitch |
| Worker data privacy | Attendance/location logged via QR | No stated data retention or privacy policy for workers | Draft a basic data-handling policy before pilot rollout |
| Expansion logic | Delhi/Aligarh → pan-India asserted | No explicit reasoning for why the model transfers | Use Section 3.4 structural-similarity argument in the pitch |
| Offline/connectivity fallback | Assumes smartphone + data access for all cleaning staff | No fallback for low-connectivity zones or non-smartphone workers | Add a basic SMS/physical-tag fallback for Phase 1 |
| SLA for unresolved tickets | Ticketing flow ends at “closed after action completed” | No defined escalation path if a ticket is not resolved in time | Define a time-bound escalation rule (e.g., 24/48 hours) to committee/admin |
| Team and execution capacity | Team named (Warisha, Maseera, Shiza, Areena, Manal) but roles not specified | No stated division of responsibility (tech/ops/finance/partnerships) | Add a one-slide team/role-ownership map to the pitch |

# 13. Legal & Regulatory Compliance

Waste management in India is a regulated sector at multiple levels, and a pitch that does not address this will read as incomplete to informed judges. The following frameworks are directly relevant to ZeroW:

- Solid Waste Management Rules, 2016 (and the updated SWM Rules effective April 2026): mandate segregation at source into (now four) streams — wet, dry, sanitary, and special waste — and assign clearer responsibility to urban local bodies for collection, transportation, and processing. ZeroW's core segregation-verification feature is a direct compliance tool for institutions and municipalities under this framework.

- Biomedical Waste Management Rules, 2016: govern the JNMCH hospital waste stream specifically; any ZeroW feature touching hospital bins must be designed to support, not interfere with, existing biomedical waste handling protocols (colour-coded bags, authorised biomedical waste treatment facilities, and CPCB/State Pollution Control Board reporting).

- Plastic Waste Management Rules and Extended Producer Responsibility (EPR): relevant to the dry-waste/marketplace revenue stream; if ZeroW facilitates aggregation and sale of plastic waste to recyclers, it should be aware of EPR registration and reporting requirements that apply to processors and, in some structures, aggregators.

- E-Waste (Management) Rules: relevant if ZeroW's e-waste awareness/collection feature expands into facilitating actual e-waste aggregation; formal e-waste handling requires routing to CPCB-authorised recyclers/dismantlers.

- Data protection considerations: attendance and location data collected on cleaning staff, and any student-identifiable ticketing data, should be handled under a basic privacy-by-design policy (limited retention, purpose limitation) even ahead of any campus-specific IT policy, and in line with India's Digital Personal Data Protection Act, 2023 once it is fully in force.

- Institutional/MoU compliance: any pilot on AMU campus or partnership with the Aligarh Municipal Corporation should be formalised through a written MoU defining data ownership, liability for missed collections, and IP ownership of the platform — not left as an informal arrangement, especially as the venture scales beyond one campus.

Note on legal advice: This section is a compliance-awareness map for pitch and planning purposes, not legal advice. Before signing any MoU with AMU, a municipal corporation, or a CSR partner, the team should have the agreement reviewed by a qualified legal professional, particularly around data ownership, liability, and IP terms.

# 14. What Else Is Missing — Additional Recommendations

Beyond the section-specific gaps already noted, the following elements are commonly expected in a complete business/social-enterprise concept document and are not yet present in the current materials:

- Risk analysis: a short table of key risks (funding delay, low student adoption, staff resistance to QR tracking, municipal procurement delays) with corresponding mitigation — judges consistently ask for this and its absence reads as a gap.

- Impact/SDG alignment: explicit mapping to relevant UN Sustainable Development Goals (SDG 11 – Sustainable Cities and Communities, SDG 12 – Responsible Consumption and Production, SDG 6 – Clean Water, given the pothole/water-stagnation point) strengthens the social-entrepreneurship framing.

- Monitoring & evaluation (M&E) framework: a small set of KPIs to track pilot success (e.g., % reduction in mixed-waste bins, average ticket resolution time, % increase in compost output) beyond the dashboard's raw data.

- Exit/scale pathway for the venture itself: whether the long-term structure is a for-profit company, a non-profit/social enterprise, or a hybrid (Section 8 structural precedent: Saahas Zero Waste began as an NGO and later incorporated a for-profit arm) — this should be a deliberate choice, not left implicit.

- Team ownership map: a one-slide breakdown of who on the team owns tech/product, operations/partnerships, finance/fundraising, and communications — useful both for internal clarity and for judges assessing execution capability.

# 15. Conclusion

ZeroW addresses a real, well-quantified problem with a capital-light, technology-enabled solution that starts on a controlled campus environment and has a credible, structurally-grounded path to municipal and pan-India expansion. Its principal strengths are the quality of its baseline data (AMU's own asset register), its phased execution plan, and its capital-light SaaS positioning relative to capex-heavy incumbents. Its principal open gaps — a fully articulated revenue and financial model, a stated competitive differentiation, an evidenced AI mechanism, and a compliance framing — are all addressable within the existing team's scope of work and have been laid out section-by-section in this document. Closing these gaps before the next pitch iteration should materially strengthen ZeroW's competitiveness in the case study/idea challenge setting.